## Paven Content Audit Plan

Collaborators: Jolene, Angie, Leif, Content team, Engineering
Purpose: Prepare Paven article content for long-term success with evolving product priorities, including vertical layout redesign, increased personalization, content optimization for brand alignment, evolving Meta employee needs, and long-term content lifestyle sustainability.

## 1. PLAN: Define the Audit Framework

Goal: Create a standardized scoring rubric and evaluation process or scope to guide a consistent, strategic audit of all article-based content within the Paven app.

Key Actions:

- Develop and document an article scoring rubric with a 10-point criteria, inclusive of:

  - Relevance to Meta employees and/or future tenants, including consideration/focus on SINKS/DINKS

  - Evergreen value

  - Recency and factual accuracy

  - On-brand with Paven’s tone and voice

  - UX adaptability (vertical layout readiness, other considerations like polls, etc.)

  - Article performance

  - Low-lift or high-lift to maintain or improve

- Align evaluation criteria with product goals, personalization roadmap, and technical limitations.

- Identify data sources to be used and considered (Looker, One Signal, Contentful, etc.)

- Establish content action categories: Keep, Update, Remove, Rewrite, Consolidate.

- Document decision logic for each category to enable audit consistency across contributors.

- Review rubric and scope with Angie and Leif for approval before proceeding.

Strategic Considerations:

- Audit should prioritize both content health and business utility, reinforcing our goal of delivering precise, empathetic, high-impact guidance to Meta employees.

- Ensure rubric supports personalization and long-term content sustainability

- Evaluation criteria must support long-term content scalability, enabling future tagging, personalization, and republishing with minimal lift.

Tactical Considerations:

- Ensure alignment across content, UX, and engineering stakeholders.

- Create an editable audit tracker in Excel for ease of use and include information from Tags 2025 spreadsheet.

- Ensure rubric is usable across all teams

### 2. ROADMAP: Timeline and Resourcing

Objective: Create a realistic, prioritized roadmap for content remediation and improvement based on audit findings. Translate audit findings into a sequenced implementation roadmap, integrating with sprint planning and the content calendar.

Actions:

- Begin content audit in terms of oldest to newest, since we know current articles are more aligned and recently touched, with the idea of retiring anything old and off-track ASAP.

- Assign reviewers (currently Jolene)

- Include task types: copy edit, UX reformat, tag update, illustration updates, etc.

- Factor in and flag dependencies like illustrations, lotties, multitenancy, benefit changes

- Integrate major content updates into our editorial calendar and additional impact needs to Jira and assign to relevant parties

Big Picture / Strategic Considerations:

- Align content efforts with seasonal moments, benefit deadlines, and product launches

- Don’t overload sprint cycles—balance quick wins with deep rewrites and make space for all team priorities

- Prioritize efforts that support user trust and app engagement

Tactical Execution:

- Use a clear naming convention for internal notes and doc versions (we should make standardizations to implement, like our new article ID system, content tags, and any other future categorizations that will be needed.

### 3. REPORT: Summarize Findings and Recommendations

Objective: Share a clear, concise audit summary that helps the broader team understand what’s working, what’s not, and where we go next. This will live in Excel.

This should outline:

- What content is working

- What needs to be removed, improved, or consolidated

- What gaps exist in the library

Actions:

- Use audit tracker tab to quantify actions (e.g., 40 Keep, 32 Update, 19 Remove)

- Highlight top-performing content by engagement, and flag underperforming content

- Identify gaps (e.g., missing content for onboarding, timely articles, new goals, etc.)

- This audit doc should live in Excel.

- Review with Angie/Leif for approval

Big Picture / Strategic Considerations:

- Use the Excel audit to create alignment around content priorities

- Use report to build momentum for improving content velocity and precision (how we manage and scale content quality)

- Consider any additional improvements planned in the future so all considerations are included in audit to eliminate extra work in the future.

Tactical Execution:

- Include line-item recommendations in the tracker for easier implementation handoff

- Flag “quick wins” and “high-value heavy lifts” to aid in sprint planning and coordinate with team

### 4. TAGS: Refine Tagging Strategy for Personalization

Objective: Ensure all content is tagged in a way that supports dynamic delivery, future segmentation, and Profile Builder personalization logic.

Actions:

- Review existing tags across article library

- Reference “CMS tagging (1).xlsx”:

  - Use ‘New tag keys’ tab to align content tags.

  - Use ‘Tags 2025’ tab for Paven links, current tags, and additional information to build the foundation of this Content Audit Excel.

- Coordinate after with Mladen or Mariano on any retagging in CMS (Contentful) or for batch updates that come up in this audit.

- Confirm all tag keys map back to Profile Builder responses.

Big Picture / Strategic Considerations:

- Accurate tagging fuels personalized recommendations, future improvements, and any dynamic comms

- Ensure consistent tagging and audit analysis to reduce rework and enable smarter filtering

Tactical Execution:

- Update the tag glossary for ongoing governance

- Keep 2025 new tags top of mind

### 5. AUDIT: Execute Full Content Audit

Objective: Evaluate every article using rubric and assign clear actions and next steps.

Actions:

- Crawl or export full list of indexable articles (see if Mladen or Mariano can provide. Not sure where the original list came from.)

- Score each article across the 10 rubric criteria (1–5 scale)

- Assign action (Keep, Update, Remove, Rewrite, Consolidate) and provide detail notes

- Include owner, last updated date, and relevancy (low, medium, high) and required lift (yellow, red, green)

- Prioritize “Keep” and “Low-lift Update” articles for vertical article launch day readiness

Big Picture / Strategic Considerations:

- Focus on preserving the content that drives value and aligns with long-term product goals

- Eliminate clutter that creates friction, confusion, or redundancy

- Keep user trust and brand credibility front and center

Tactical Execution:

- Annotate as you go: highlight links that need updates, mentions of dated programs, accessibility red flags

- Use conditional formatting in the audit sheet to highlight critical actions

## Audit Success Looks Like:

- All content having been reviewed

- A focused, mobile-optimized, high-impact content library

- All launch-critical articles are accurate, scannable, and aligned with our voice

- Every article is tagged in a way that supports Profile Builder, content tags, and personalization

- A prioritized roadmap for improvements post-launch

- A culture of proactive content health management, not reactive cleanup

- A clear path forward

Basic Paven Audit Concept – This will be an Excel sheet

Paven Content Audit Rubric

Use this rubric to evaluate whether a piece of content should:

- Stay as-is (Keep)

- Be updated (minor or major) (Update, Rewrite)

- Be removed or consolidated (Consolidate, Remove)

Each criterion is rated 1–5. Add optional tags at the end for metadata tracking.

| Criteria | What to Evaluate | Score (1–5) |
| --- | --- | --- |
| 1. Relevance to Meta Employees | Does this content directly support Meta employees’ financial wellness, benefits, or life/work needs? (e.g., RSUs, fertility, mindfulness, relocation)? Or if we have a targeted company for future tenancy, does it align with theirs? |  |
| 2. Evergreen Value | Is the topic timeless or easily adaptable for year-round use? Avoids time-sensitive terms or expired references. |  |
| 3. Recency & Accuracy | Has this piece been updated in the past 6–12 months? Are stats, links, dates, and program names current and trustworthy? |  |
| 4. Strategic Alignment | Does the piece align with Paven’s voice and pillars (mindfulness, personalization, emotional and financial wellbeing)? |  |
| 5. UX & Layout Readiness | Is the structure mobile-friendly, easy to vertically scan, and optimized for bite-sized consumption in a mobile-first design? |  |
| 6. Content Performance | Indexed and ranking? Does it have internal/external links, optimized metadata, and is it free of duplication or keyword cannibalization? |  |
| 7. Organic Engagement | Does it show traffic, engagement, scroll depth, low bounce rate, or strong time-on-page (use Looker, One Signal, etc.)? |  |
| 8. Technical Health | Does it load successfully? Any items broken in the article? Lotties too large or images broken? Links all work? Action items at the end are relevant and load? PageSpeed acceptable for mobile? |  |
| 9. Effort to Update | How much lift is required to bring this to a publishable state (copy, illustration, lottie, benefit updates, missing data)? |  |
| 10. Business or Lifecycle Value | Does it map to user journey stages and access (e.g., onboarding, profile builder, goals, journeys)? Is it tied to important business goals or features? |  |

### Total Score Guidance:

- 45–50: Keep As-Is – High-value, performance, and ready for re-use or boost.

- 36–44: Light Refresh – Minor copy tweaks or design formatting.

- 26–35: Moderate Update – Needs new data, copy overhaul, or partial redesign.

- 15–25: Rewrite or Consolidate – Salvage useful parts or blend with stronger content.

- Below 15: Remove – Low-value, outdated, or irrelevant.

### Optional Tags / Metadata Fields (for spreadsheet use):

- URL

- Owner

- Date Published or Last Reviewed

- Tags/Groups

- Analytics Traffic (past 90 days)

- CTA (Yes/No)

- Duplicate Flag

- High Lift Flag (Design/Benefit Review needed)

- Top Performer: Past engagement was high (include metric if known)

- Unique ID

- Series Piece: Part of a larger content thread

- SEO or Keyword Asset: Ranks or indexed well for search terms

- Redundant: Overlaps significantly with another piece

### 3 Action Categories (Dropdown in Dashboard):

- Keep

- Update (Which items—illustrations, lotties, info, etc.)

- Remove

- Rewrite

- Consolidate

### Details (Freeform Notes):

Explain what to update, consolidate, or remove.

Examples:

- Is this still accurate? Not sure of the IVF offerings currently.

- Combine with /planning-for-parenthood for stronger performance

- Illustrations don’t feel cohesive

Questions:

What are things we need to look for for vertical layout?