## Running priority list
Priority | Ad-hoc | Added | Updated | Status | Next milestone target | Area of app | Theme | Type | Mladen | Mariano | Leif | Angie | Jolene | Michael | Vitto | Gloria | Nadia | Brian | Scotty | Haila | Ambar | Aparna | Karishma | Wassim | Neeli | Raga | Kota | Mahesh | tbd
| User content ratings |  |  |  | deployed Jan | Content | Understand audience | Enhancement |  | S |  |  |  |  | P | [5 empty] | P | P | P | P | P | P | P
| Removed char. limits in articles |  |  |  | deployed Jan | Content | Admin | Enhancement
| Playstore compoliance |  |  |  | deployed Jan
| Android deeplink |  |  |  | deployed Feb | Comms | Reduce friction | Bug fix | [16 empty] | P
| iOS rating bug |  |  |  | deployed Feb | Content | Understand audience | Bug fix | [13 empty] | P
| redirect to splash if SSO fails |  |  |  | deployed Feb | Log-in | Reduce friction | Bug fix
| Tags limit removed |  |  |  | deployed Feb | Content | Admin | Bug fix | P
| Poll creation UI |  |  |  | deployed Mar | Content | Admin | Enhancement | P
| iOS video issue |  |  |  | fixed in Mar | Content |  | Bug fix |  | P
| Poll data in Looker (+ by User) |  |  |  | deployed Mar | Content | Data quality | Enhancement | P
| Image not centered Feature space (web) |  |  |  | ready for deploy Mar | Content |  | Bug fix
| External links Suggestion iOS (some scenarios) |  |  |  | ready for deploy Mar | Content |  | Bug fix
| Goals & vehicle caching |  |  |  | ready for deploy Mar | Goals |  | Bug fix
| Poll - image centering |  |  |  | ready for deploy Mar | Content
| Poll - Suggestion Title & description |  |  |  | ready for deploy Mar | Content |  | Bug fix
| Figure out missing tenant in Auth0 | 2025-03-25 |  |  | Mladen found Auth0 had a few hour outage | Log-in |  | Bug fix | P |  | S
| Content tags overwrritten each read | 2025-03-25 |  |  | Mladen fixed Mar26 | Content | Personalization | Bug fix | P | S
| Renewal of Paven.io domain | 2025-03-27 |  |  | Renewed Apr1 | Infra | Admin
| Roundfeather.com can't send to gmails | 2025-03-31 |  |  | Leif emailed UST IT, got fixed | Infra |  | Bug fix
| Finalize profile questions |  |  |  | finalized Ap2 | Profile | Personalization | Enhancement |  | S | S | P | S
| Vertical article layout test |  |  |  | test complete, results Apr7 | Content | Reduce friction | Enhancement | [6 empty] | S |  |  |  | P | S
| Upcoming release prep & UAT |  |  |  | all platform in stg, few bugs; target submit Apr4, release Apr7 | Profile | Personalization | Enhancement | P | S |  |  |  |  | S | [5 empty] | S | S | S | S | S | S | S
| Q2 product planning |  |  |  |  | Infra |  | Ops |  | S | P | S
| Q2 content planning | [6 empty] | Ops |  |  |  | P
| Multi-tenancy plan refresh |  |  |  | resources to Smitha Ap2, meeting GCP expert Apr7 | Infra | Admin | Enhancement | P | S | S
| App crashing in card carousel | 2025-04-10 |  | Done | hot fix Apr16
| Tags for library |  |  | Done | Done | Content | Personalization | Enhancement |  |  | A | A | R
| Content defects on Profile builder | 2025-04-10 |  | Done | presumably due to caching, but let's keep an eye | Profile | Reduce friction | Bug fix
| GW sunsetting - i18n |  |  | Done | Done | Infra |  | Enhancement | A | [11 empty] | R
| Poll data dashboard |  |  | Done | Target Apr4 | Data | Data insights |  |  | R
1 | Investigate Event limits on OneSignal | 2025-04-20 | 2025-05-13 | Done | leif did call with OS sales, might not upgrade; mLaden to update the Event streams to exclude Sent/Received | Data | Data insights | Ops
17 | Flutter POC |  |  | Done | Next is try Polls on Flutter | Infra |  | Enhancement | A
2 | Profile builder edit change | 2025-04-25 | 2025-05-13 | Done | Hot fix release late May |  |  |  |  | A | A | A |  |  | R
3 | External link not working Suggestion Android | 2025-04-03 | 2025-05-13 | Done | Hot fix release late May | Polls | Reduce friction | Bug fix |  | A
4 | Polls external link iOS (not articles) | 2025-04-17 | 2025-05-13 | Done | Hot fix release late May | Polls | Reduce friction | Bug fix |  | A
5 | Token expiry to avoid re-logins |  | 2025-05-13 | Done | Hot fix release late May | Log-in | Reduce friction | Enhancement |  | A | [11 empty] | R
6 | Logged Out Error handling on Web |  | 2025-05-13 | Done | Hot fix release late May | Log-in | Reduce friction | Bug fix |  | R | R
7 | Dashboards. - clicks by list |  | 2025-05-19 | Done | Mariano working on it May19-20 | Data | Data insights | Enhancement | A | R
4 | Finalize June-July roadmap | 2025-05-07 | 2025-05-27 | Done | See the Cross Team plan tab |  | Admin | Ops
11 | Manage VAPT | 2025-03-26 | 2025-05-19 | Done | Report delivered 5/19 | Infra | Admin | Ops | R |  | A
| Views + Likes in Contentful per article | 2025-05-27 | 2025-05-28 | Done |  |  | Data insights |  | R
36 | Go in backend experiment |  | 2025-05-28 | Done | released with Config goals | Infra | Reduce friction | Enhancement | R
31 | Content gating scoping |  | 2025-05-28 | Done | Ambar looking at Search impact; 3 sprints BE, 1FE | Content | Personalization | Enhancement | R | A | A
7 | Newsletter click discrepancy |  | 2025-05-29 | Done | Still don't know why Branch is different than OneSignal but now doing Funnel dashboard | Comms | Data quality / Login | Bug fix | A | R | A
1 | OneSignal data in Looker |  | 2025-05-13 | Done | Removing Sends/Receives; trying to tie users who Open to behavior in the app | Data | Data quality | Ops | R | A
18 | Vertical article layout detailed scoping engineering |  | 2025-05-13 | Done | Mariano double checked with Mladen/Vitto; the estimates are realistic, no add'l India team esimtaes req'd | Content | Reduce friction | Enhancement | R | A
2 | GCP cost reductions BE changes | 2025-05-05 | 2025-05-28 | Done | Mladen wrapping up week of May26 |  | Admin | Ops | R |  | A
31 | Content audit pt1(tagging for profile builder) | 2025-03-03 | 2025-05-07 | Done | Jolene completing wk Apr2 | Content |  | Ops |  |  |  |  | R
11 | Under maintenance modal | 2025-04-29 | 2025-05-30 | Done | target completion Jun1 | [6 empty] | R |  |  | R
11 | Profile builder promotion prep | 2025-04-15 | 2025-06-06 | Done | Michael/Nadia on video | Profile | Personalization | Enhancement |  | R |  | A
2 | Key missing for ASAP goal ProjectedDate with no vehicles | 2025-03-21 | 2025-06-02 | Done | bug created - to be deployed with the BAC release PT-5519 | Goals | Reduce friction | Bug fix |  | R |  |  | A
8 | Background color on suggestions for polls (Jira ) | 2025-06-06 | 2025-06-17 | Done | Deployed Jun17
9 | Video not running on iOS troubleshooting | 2025-05-29 | 2025-07-30 | Done | Mariano sent more details to bitmovin support
6 | Plan for VAPT remediation | 2025-06-06 | 2025-07-01 | Done | waiting for more direction from IT Security | Infra | Admin
10 | Q3 content calendar | 2025-06-06 | 2025-07-02 | Done | brainstorms done 6/12; Angie doing planning | Content | Admin
3 | Data snapshot of Profile | 2025-06-30 | 2025-07-07 | Done | sprint 82 | Data | Data insights
| Behavior for malicious search | 2025-07-09 | 2025-07-10 | Done | go with least effort, like 'No results' or whatever results. No special modal
| Android logged out too often | 2025-07-10 | 2025-07-11 | Done | Mladen hadn't made update to UST/RF, just Meta for extended refresh tokens
| can we add ages to the profile data | 2025-07-11 | 2025-07-17 | Done | will be avail 7/15
| Android sign-off behavior (maybe Pushes) | 2025-06-20 | 2025-07-21 | Done | Mladen will work with Manoj | Log-in | Reduce friction | Bug fix
| Add 'Group-Childfree' tag |  | 1901-12-21 | Done | changed from 'topic-childfree' to 'group-childfree' |  | Personalization
| Test the 'loss of internet' on refresh tokens | 2025-06-23 |  | Done | Mladen made a change for USt - tested on iOS & Android 7/21 | log-in | Reduce friction | Bug fix
14 | Angie doing an AI review of One Signal data | 2025-06-09 |  | Done | Angie got a new formula for writing the push text | Comms
1 | Update Sendgrid limits | 2025-06-06 | 2025-07-01 | In progress | Mladen sent approval to Google for transfer but it doesn't seem to be processed | Comms | Admin | Bug fix
2 | Automate creation of branch.io links | 2025-06-04 | 2025-07-02 | BLOCKED | getting the API feature is $3k/mo package; Mladen to explore other way to get link tracking data | Comms | Admin | Enhancement
3 | Polls visual issues on Android | 2025-07-10 |  |  | Mladen to give to manoj
9 | Finalize first dynamic comms | 2025-05-23 | 2025-06-06 | In progress | priority seems good, angie working on the messaging | Comms | Personalization
4 | Q3 plan | 2025-06-30 |  | In progress
5 | Add results from Profile to looker | 2025-06-23 |  |  | likely after BAC goal and One Signal release | Data
6 | Auth0 consolidation under 1 tenant (VAPT fix) |  | 2025-07-01 | In progress | consolidate and make annual in April; might help with VAPT issue | Infra |  | Ops | R |  | A
7 | Segregation of tenant data (namespace) | 2025-07-02 | 2025-07-21 | In progress | in progress for User Data; then later Goals and Vehicles | Infra
8 | Newsletter funnel Dashboard in Looker | 2025-05-29 |  | In progress | Mariano & Leif made first pass, hope to present on Sprin review Jul2 | Data | Data insights
10 | Null values bug |  | 2025-05-27 | In progress | Sendgrid, automated branch, and release too priority; now for wk of Jun19 | Data | Data insights | Bug fix | A | A | [11 empty] | R
11 | Silent SSO on web |  | 2025-05-27 | BLOCKED | no substantive feedback from community; don't think it's a Meta problem; need to take a step back on our strategy; to prepare Ambar/Mladen need to research a little more with Auth0 | Log-in | Reduce friction | Enhancement | A |  | A | [9 empty] | R
12 | Redo the marketing site for Paven | 2025-06-25 |  |  | Vitto to create design; Mladen to schedule with India |  | Admin
13 | Content audit FULL | 2025-03-03 | 2025-06-06 | In progress | Angie reviewed outline and process; going back to draft Audit article library for relevancy, audience segment, style/voice/tone, topics, update needs, illustration sizing, etc. | Content | Admin | Ops |  |  |  |  | R
15 | Research panel interviews | 2025-02-28 | 2025-06-06 | BLOCKED | trouble getting volunteers | Data | Understand audience | Ops |  |  |  | A | [6 empty] | R
16 | Prioritize poll enhancements | 2025-05-19 | 2025-06-06 | In progress | Leif to bring to team next week (Jun9+) | Polls | Admin | Ops
17 | Review platform limits (OneSignal, Branch, etc) | 2025-05-30 | 2025-06-06 |  | likely sprint 81. Bitrise, Auth0, Datadog | Infra | Admin
18 | Style guide | 2025-05-07 | 2025-05-07 | In progress | Jolene in progress; Angie to review soon for audit needs | Content | Quality | Ops
19 | Investigate custom AI for Paven (internal use) | 2025-06-13 |  |  | Leif to ask Smitha; Angie asked Shubhendra; Brian looking into it as well
20 | Investigate why Android OTP code is slow to send | 2025-06-12 |  |  | mladen possibly sp81-82 | Log-in | Reduce friction
21 | Transfer ownership of PlayStore and AppStore from RF to UST | 2025-06-18 |  |  | waiting for after VAPT release (July-ish) | Infra | Admin
22 | Publication process documentation | 2025-05-07 | 2025-05-07 | In progress | Jolene in progress; likely will put this on hold for other priorities | Content | Efficiency | Ops
23 | Strategize for Splash fall-off (24%) | 2025-06-13
24 | Strategy for NEW user effort (email, Home, One Signal) | 2025-06-09
25 | Create Home experience ('Featured') for NEW users | 2025-06-09
26 | Draft an email for users who are not signed up | 2025-05-29 | 2025-06-06 |  | sprint 81 | Comms | [5 empty] | R
27 | Investigate deleting duplicate/inactive users from One Signal | 2025-06-16 |  |  | users who got a new phone might be counted twice, as an example
28 | CMS enhancements requirements | 2025-05-07 | 2025-06-06 | Not started | Angie to start Sp81; Content team to document requirements | CMS | Efficiency | Ops
29 | Deeplinks opened on iOS/Android don't detect app | 2025-06-02 |  |  | Mladen to look into after Profile builder release |  |  | Bug fix
30 | Seed OneSignal with existing user profile status |  |  |  | probaby sprint 81
31 | Automate update of user profile completion status in OneSignal | 2025-05-27 |  |  | India tentative start for Jun 12
32 | Release prep - configurable goals |  |  |  |  | Goals | Personalization | Ops | R | R | [11 empty] | R
33 | Reminder to include AI and Experiments in Sprint Review | 2025-06-06
34 | Investigate AI tool for resizing images |  | 2025-06-06 | In progress | Vitto will write-up the outcome of investigation; Brian has some ideas on this |  |  | Ops |  |  | A |  |  |  | R
35 | Bug - slow loading of newsletter links (both web/iOS) to Paven content | 2025-04-29 |  |  | QA to look at it; created a ticket for Mariano |  |  |  |  | R | A |  |  |  | R
36 | Migrate Jira to Azure Boards | 2025-06-06
37 | Content process optimization | 2025-05-30
38 | Suggestions/CTA enhancement requirements | 2025-05-07 | 2025-05-07 | Not started | TBD - could we make this a design project soon? | Content | Engagement | Enhancement
39 | Vehicles not appearing in Wallet/budget | 2025-03-31 |  |  | likely right after BAC release | Budget |  | Bug fix
40 | Domain migration |  |  |  | Blocked by VAPT | Infra |  | Ops | R |  | A
41 | Add repliable email to newsletter | 2025-03-26 |  |  | depends on domain migration
42 | In-app form template | 2025-04-03 |  |  | quick feasibility with Mladen/Mariano, consider for design after Wellness Score
43 | Content Gating POC on Contentful | 2025-05-01 |  |  |  | Content | Personalization | Enhancement | R
44 | No Internet error message | 2025-05-28 |  |  | Mladen going to investigat if easy fix
45 | OneSignal in-app notifications |  |  |  | Mariano defining triggers |  | Reduce friction | Enhancement |  | R
46 | Goals QA | 2025-03-01 |  | Not started | Angie to gather old notes | Goals | Reduce friction | Bug fix |  |  | A | R
47 | Script to push content prod<>stg | 2025-03-25 |  |  | most valuable for Vertical article implementation | Content | Admin | Enhancement | R
48 | Content resource needs for multitenancy | 2025-05-30
49 | Way to guage interest in 30day challenge | 2025-04-03 |  | In progress
50 | Explore manual COHORTS | 2025-04-01 |  |  | phase 2 of Dynamic Comms | Data | Personalization | Enhancement
51 | Audience definition exercise | 2025-04-01 |  |  |  | Data
52 | update Nav with centralized polls
53 | Nav / IA test |  |  |  |  | Nav | Reduce friction | Enhancement | [6 empty] | A |  |  | R | A | A
54 | Journeys strategy updates | 2025-05-07 | 2025-05-07 | Not started | Document collections requirements for new IA landinng pages
55 | Collections strategy updates | 2025-05-07 | 2025-05-07 | Not started | Document collections requirements for new IA landinng pages | Content | Personalization | Enhancement
56 | Data pipeline - Backend count of how many times the article was presented (not aggregated by user) | 2025-03-27
57 | Review current Alerts - baseline what we have vs need |  |  |  | define what this is | Infra |  | Enhancement | R |  | R
58 | Vendor migrations |  |  |  |  | Infra |  | Ops | A |  | R
59 | Engagement Deep Dive |  |  |  |  | Data | Data quality | Ops |  | A | R | A | A
60 | Content analytics approach |  |  |  |  | Data | Data quality | Ops |  |  | R |  | A
61 | Wellness Score exploration |  |  |  |  | Profile | Personalization | Enhancement |  | A |  | A |  |  | R
62 | Confluence migration |  |  |  |  | Infra |  | Ops |  |  | R
Note on F27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Angela King(UST,US) This is what you mentioned in teams about crashing when looking for Jolene's article. Can you pls create a jira ticket with as much detail as possible, including platform, user, approximate time, the page, the behavior or circumstances leading up to the error, the error screen (or just crash?)
Note on F45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mariano Coni(UST,AR) Just caught up with Angie and she pointed out that Branch is also behaving strangely, not lining up with OneSignal. can we include that into our investigation?
Note on F52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mariano Coni(UST,AR) Were you able to get an update on this bug?

## Cross team plan 2025
| Sprint 74 | Sprint 75 | Sprint 76 | Sprint 77 | Sprint 78 | Sprint 79 | Sprint 80 | Sprint 81 | Sprint 82 | Sprint 83 | Sprint 84 | Sprint 85 | Sprint 86 | Sprint 87 | Sprint 88 | Sprint 89 | Sprint 90
Start date | 2025-03-13 | 2025-03-27 | 2025-04-10 | 2025-04-24 | 2025-05-08 | 2025-05-22 | 2025-06-05 | 2025-06-19 | 2025-07-03 | 2025-07-17 | 2025-07-31 | 2025-08-14 | 2025-08-28 | 2025-09-11 | 2025-09-25 | 2025-10-09 | 2025-10-23
Releases (tentative) | 2025-03-27: Profile builder +; 2025-04-24: BAC goal +; 2025-05-22: TBD; 2025-08-14: VAPT release #1; 2025-08-28: Config goals release; 2025-09-11: VAPT release #2
Key Events & Client support | bar: 2025-10-09
India FE devs (roughly) | Silent SSO web Profile builder + Null analtycs Token expiry | Profile builder + Null analtycs | * BAC goal * bug fixing | * BAC goal * bug fixing | * Profile builder edit * bug fixing | * Profile builder edit * bug fixing | * Config goals * Other bug fix | * Config goals * other bug fixes - nulls | * VAPT fixes, pt1 * BE rules for OneSignal | * VAPT fixes, pt1 * In-app deeplinks * Flutter POC | * VAPT fixes, pt2 * Flutter comp. libr * Config goals release prep * Android api version | * VAPT fixes, pt2 * Flutter comp. libr * Config goals fixes | * VAPT fixes, pt2 * Flutter Nav/Home * In-app deeplinks | * Flutter Nav/Home | * Flutter Nav/Home | * Polls enh Content gating FE | * Polls enh | * Polls enh | * Polls enh | * Vertical articles * bug fixing | * Vertical articles * bug fixing | * Vertical articles * bug fixing | Wellnes Score | Wellness Score | Nav / IA | TBD
Mladen, Ambar & Mahesh | * Silent SSO * Go experiment * GW sunsetting | * Multi-tenancy prep * Domain migration * GW sunsetting | * Go backend changes * bug support & hotfix | * Go backend changes * Analytics - polls & lists data | * OneSignal exploration * script for CMS prod-stg | *release prep * null users * GCP cost reduction * VAPT remediation * OneSignal investig. | * release prep BAC * VAPT plan * Automate branch links | * VAPT plan * upgrade sendgrid limits * Auth0 for VAPT * BE rules framework for OneSignal | * Auth0 for VAPT * segregating tenant data (namespace) *snapshot of profile data * BE rules for OneSignal | * Auth0 for VAPT * ETDC exploration * Content gating. & content refactor | * Content gating. & content refactor * playstore / appstore transfer * Profile data in Lkr | * Content gating. & content refactor *Auth0 consolidation * vehicle/wallet fix BE | * Content AI search * prep for new FE work in flutter | * prep for new FE work in flutter * null values | * prep for new FE work in flutter | Multi-tenancy | Multi-tenancy | Multi-tenancy
Design | * Profile builder UAT * Test prep | * Vertical article prep * BAC UAT | * Vertical article prep * BAC UAT | *Profile builder edit tweak * BAC UAT | * Polls enh * support & UAT | * Polls enh * support & UAT | * Polls enh * support & UAT | * Polls enh * support & UAT * 1pager | * Polls enh * support & UAT | In-app feedback form | Vitto only 25% | Vitto only 25% | Vitto only 25% | *Wellness Score | *Wellness Score | * Address gaps in Personalization | * Address gaps in Personalization
Product | 2025-03-13: * Q2 planning * Release prep * Newsletter discrep.; 2025-03-27: * Multi-tenancy prep * Wellness Score; 2025-04-10: * Multi-tenancy prep * Wellness Score * Release prep; 2025-05-08: *Profile builder * Vertical article * Secondary research; 2025-05-22: * Polls enh * support & UAT * VAPT * OneSignal strategy; 2025-06-05: * Polls enh * support & UAT * VAPT * OneSignal strategy; 2025-08-28: * Wellness Score
Research (tracker) | 2025-03-13: Research panel; 2025-05-08: DINKs,SINKs, HENRYs secondary; 2025-05-22: Research Panel; 2025-06-05: Research Panel Childfree workshop
User testing | 2025-03-13: Vertical Article; 2025-03-27: Vertical Article; 2025-06-05: * Polls enh; 2025-07-17: * Polls test 2; 2025-07-31: Nav / IA; 2025-09-25: Wellness Score
Analytics | 2025-03-13: * Content analytics
Publications (tracker)
Communications
UX content | 2025-03-13: * Test prep * Tags for library; 2025-03-27: * Wellness Score; 2025-04-10: * Wellness Score; 2025-04-24: * Wellness Score
Motion designer
Changelog
[5 empty] | TBD Content Gating Nav / IA Vertical article Polls enh Wellness Score | Design Insurance Estates Dashboard Wallet enh
Prod
[11 empty] | User service | By Jul31
[11 empty] | Content tweak | By 1st wk of Aug
[11 empty] | 2 initial rules | 2nd wk of Aug
[11 empty] | Testing with UST users | 2nd wk of Aug | 1 rule has a 2wk retrigger
[11 empty] | First push to Meta | 3rd wk of Aug | can be a subset of users (in the rule, not OneSignal)
Next rule
Note on A1: @suzannevanbeek@roundfeather.com _Assigned to suzannevanbeek@roundfeather.com_ -Leif Drake

## Ongoing
Ongoing
Continuous publication cycle | [5 empty] | P | P | P |  | P | P
Client management |  |  |  |  | P | P | S | S
Reporting up to Evolv leadership |  |  |  |  | P | P
Billing and vendor management |  |  |  |  | P
Content Analytics review |  |  |  | S | S | S | P
App enagement review |  |  |  | P | S | S
Design backlog
Action card UX design | Nav | Reduce friction | Enhancement | [5 empty] | P
Buying a car design | Goals |  | Enhancement | [5 empty] | P
UI bug fixing | Nav |  | Bug fix | [5 empty] | P
Nav / IA design | Nav |  | Enhancement | [5 empty] | S |  |  | P
Vertical article design | Content | Reduce friction | Enhancement |  |  | S |  |  | P
White Label exploration | Nav |  | Enhancement | [5 empty] | P |  |  | S
Centralized polls / Dynamic conclusions

## Cross team plan 2024
| Sprint 42 | Sprint 43 | Sprint 44 | Sprint 45 | Sprint 46 | Sprint 47 | Sprint 48 | Sprint 49 | Sprint 50 | Sprint 51 | Sprint 52 | Sprint 53 | Sprint 54 | Sprint 55 | Sprint 56 | Sprint 57 | Sprint 58 | Sprint 59 | Sprint 60 | Sprint 61 | Sprint 62 | Sprint 63 | Sprint 64 | Sprint 65 | Sprint 66 | Sprint 67 | Sprint 68 | Sprint 69 | Sprint 70 | Sprint 71 | Sprint 72 | Sprint 73 | Sprint 74 | Sprint 75 | Sprint 76 | Sprint 77 | Sprint 78 | Sprint 79
| Dec 21 - Jan 4 | Jan 4 - Jan 18 | Jan 18 - Feb 1 | Feb 1 - Feb 15 | Feb 15 - Feb 29 | Feb29 - Mar14 | Mar14- Apr4 | Apr4 - Apr11 | Apr11-Apr25 | Apr25-May9 | May9-May23 | May23-Jun6 | Jun6-Jun20 | Jun20-Jul4 | Jul4-Jul18 | Jul18-Aug1 | Aug1-Aug15 | Aug15-Aug29 | Aug29-Sept12 | Sept12-Sept26 | Sept26-Oct10 | Oct10-24 | Oct24-Nov7 | Nov7-21 | Nov21-Dec5 | Dec5-19 | Dec19-Jan2 | Jan2-16 | Jan16-30 | Jan30-Feb13 | Feb13-27 | Feb27-Mar13 | Mar13-27 | Mar27-Apr | Apr | Apr | May | May
Releases (tentative) |  | All platforms - Jan 1 - Home, FF |  | Mobile - Feb 7 - Explore, Benefits, Coaches Web - Feb14 - Explore, Benefits | [5 empty] | Journey helper Apr 29 |  |  |  | DoB text key |  |  | Estimated Aug12 -BAH goal -Retirement goal -Brokerage ??User content ratings |  |  | Sept29-30 Detch vehicles - BAH, Retire, Brokerage EMF goal & Checkings/Savings Goal setups (partial) - Retire/EMF | [5 empty] | Dec3 - SSO, hyperlinks, user content rating (mobile), |  |  |  |  | SSO - web & android | Profile Builder
Key Events & Client support | FF booking launch Jan1 | [7 empty] | Meta company-wide post Apr17 |  |  | Remove Life@ logo |  |  |  | Jul30 - newsletter
A1 Maint. Eng (roughly) | Home & Main Menu Bug fixing contract ends Dec31 | Web dev on PTO (2wks) Explore, Benefits, Coaches (mobile) Error handling (BE) prep | Explore, Benefits (Web) Hide 'Views' of articles (Web) Search page (Web) Journeys (mobile & BE) Xcode 15 (iOS) Fixing Kogito rules (BE) | Journeys (all) ARG/UY holidays Feb 12&13 | Journeys (all) | Journeys 'nice-to-have' - Video on selection page - New tool pop-up - Option: remove, preview, share - Toast after article read | Android dev PTO Mar18-22 Argentia holidays Mar 28&29 Finish Journeys Android -Life Path bug, +? BE - Fix kogito goal bug - Keyword search: sort by relevance and improve latency - groom & size BE Action Card Enh | Finishing Journeys POC on detach vehic graph Estimating DV work | Small bug fixes Journeys FE - Break apart BaH - adjust calls for brokerage BE -Kogito (ongoing journey) - Kogito (available journeys and none ongoing) - Journey Feature Toggle | FE - Break apart BaH - adjust calls for brokerage BE - Fix Kogito rules - Action card enhancements?? | FE - Break-apart Retirement - adjust calls for all retirement vehicles BE - Fix Kogito rules - Fix Search performance - Action card enhancements?? | FE - Brokerage visuals - graph & assign goal BE -Node update for Web | FE - Brokerage visuals - graph & assign goal DoB text key BE -Error handling | Contract Ends Jun 30 Detach veh phase 1 | Detach veh phase 1 | Detach veh phase 1 | First new vehicle prep Checkings implementation | Detach Vehicl UAT fixes Savings implementation First new goal prep | Onboarding new team EMF goal - setup and dashboard | Contract ends Aug30 Onboarding new team Android bugs i18n loading issues Analytics: collections, lists Setups for EMF and Retirement goals | India team starting User content ratings Lazy SSO | India team starting India -User content ratings A1 -Lazy SSO -goals refactor | India -Profile builder A1 *goals refactor | India * user content ratings - mobile A1 * goals refactor - mobile |  |  |  | India * Profile builder - mobile * user ratings - web * Goals refactor web - ambar | * Profile builder - mobile * user ratings - web * Goals refactor web - ambar | * user ratings - web * Goals refactor web - ambar |  | * Page-to-page - mobile * Page-to-page - web | * Page-to-page - web * Polls revisitable - mobile | * Polls revisitable - mobile * polls revisitable - web | * polls revisitable - web * content gating | * content gating Wellness score | Wellness score |  |  | Insurance dashboard | RSUs | RSUs | Buying a car FE | Wallet & new vehicle cards | Wallet & new vehicle cards | Budget - change list of goals to vehicles | Wellness Score in UI BE improvements
RF Engineering | Pre-prod enviro (Mahesh +) Detach vehic (Mladen) Vacation Mladen / Vishal | Vishal PTO Jan15-19 ES fixes and doc (JD & Vishal) SSO fix (Vishal) Detailed design and plan for detach veh (Mladen) Pre-prod enviro (Mahesh & JD) | Detach veh (Mladen) - detailed plan & design Analytics pipeline (JD) - Onboarding & Wellness Score + more ES fixes (Vishal) Error handling (BE) (Vishal) - MVP | Detach prototype (Mladen & team) - possibly Brokerage shared by 2 goals One signal (Vishal) - File load automation - new tags ES testing (Vishal) - observe code during test | Detach proto (Mladen & team) | Detach proto (Mladen & team) | Detach proto (Mladen & team) | Documentation of Detach vehicles Back-end service stuff Search results load | Data pipeline - Journeys Automate load of content tags | Vishal resigning end of Apr Detach veh (pt 2) (Mladen) - Checkings - Savings | Detach vehicles, pt1 - Consolidate 7 serivces to 1 Data pipeline -App onboarding events | Detach vehicles, pt1 - Consolidate 7 serivces to 1 (Mladden) | Supporting A1 on pt1 (Mladen) Action card enh (JD) | Supporting A1 on pt1 (Mladen) Action card enh (JD) | Supporting A1 on pt1 (Mladen) | Supporting A1 on pt1 (Mladen) Fix goals content lists Interviewing India team | Supporting A1 on pt1 (Mladen) Interviewing India team | Checkings/EMF/Savings (Mladen) Null users in reporting Analytics: Users not in the user file | Checkings/EMF/Savings (Mladen) Adding data for source of user (newsletter, etc) Null users in reporting | Newsletter sign-up page Force log out users not in file Null users in reporting | Investigate Silent Authentication for SSO Services Implementation Integration testing | *goals refactor *Service discovery | *Backstage *Service discovery |  | Wellness Score review - add BAH to the calc - Fix no debt same as bad debt - Data validation |  |  | Search -Index Vehicles/Goals Budget Multi-tenancy support
Design | Journey Helper (Vitto) -Iteration design Account Linking & Detached vehicles (Vitto) Buying a car (Charlie) - Figma doc | Journey Helper (Vitto) -Design iteration, esp Web RSU vehicle (Charlie) - RSU review of figma (Vitto) Journey illustrations(Charlie) - Backgrounds x 4 - Celebrations x 4 | Detached vehicles (Vitto) - Design iteration Journey Helper (Vitto) -Figma documentation RSU vehicle (Charlie) - Figma documentation Savings illustrations (Charlie) | Detached vehicles (Vitto) - Design iteration, prototype, web designs Savings vehicle - figma documentation (Charlie) User content ratings (Charlie) - Exploration RSU (Charlie) - incorporate user feedback | Charlie supporting UST deck Detached vehicles (Vitto) - Design for EMF, Savings, Checkings EMF goal (Vitto) Savings & Checkings (Vitto) - Iteration | Charlie supporint UST 1wk Savings & Checkings (Vitto) - Finalization Detached vehicle (Vitto) - backtrack designs to savings, checking, brokerage, bah, retirement, emf RSU Detached Vehicle Friendly (Vitto) - design updates Journey Helper (Vitto) - Dev Support Buying a car (Vitto) - Detached vehicle friendly | Charlie supporting UST Vitto PTO Mar21-22, 28-29 Journes (Vitto) - UAT Support Mock-up for strategy deck (Vitto) - Insurance, Goals trade-offs Detached vehicle (Vitto) - inform user of change of target dates - backtrack to bac, bah, retirment, emf, saving, checking, rsu, brokerage | Charlie on UST Insurance dashboard (Vitto) - Exploration Detached vechiles (Vitto) - Dev support RSUs (Charlie) - incorporate user testing Illustrations (Charlie) - Suggestions page web - Benefits page web | Charlie on UST Insurance dashboard (Vitto) - iteration User content ratings (Vitto) - Finalization | Charlie on PTO UX Detached Vehicles (Vitto) - slow loading - update to magic number Insurance dashboard (Vitto) - Iteration | Charlie on Leave Profile builder (Vitto) -Exploration | Charlie on Leave Profile builder (Vitto) -Proto of mobile | Charlie on Leave Profile builder - iteration & prototype CMS benefit content standardization - Cover image (Vitto) - Titles and CTAs (Michael) Insurance dashboard (Vitto) - Iteration | Vitto on PTO Jun24-Jul5 Dev support RSU content (Michael) - Finalization | Profile builder (Vitto) - Figma finalization Page-to-page UX (Vitto) - Exploration Insurance dashboard (Vitto) - Iteration | Page-to-page UX (Vitto) - Iteration Insurance dashboard (Vitto) - Mobile & final web Detach Veh support - | Page-to-page UX (Vitto) - Finalziation Multi-tenancy audit (Vitto) | Estates dashboard (Vitto) | Estates dashboard (Vitto) Benefit provider collections (Vitto) | Estates dashboard (Vitto) Wrap up with A1 HSA vehicle (Vitto) - illustrations for gloria Dev support | VItto on PTO Sept25-Oct5 Wrap up other projects Dev support | Wellness Score (Vitto) -Iteration Dev support | Wellness Score (Vitto) -Iteration Dev support | Wellness Score (Vitto) -Finalization Dev support | Wellness Score (Vitto) -Finalization Dev support | Vertical article layout (Vitto) | Polls revisitable | Polls revisitable | Wellness Score | Wellness Score | Wellness Score | Dashboard | Dashboard | Wallet + Net worth chart (Vitto) Illustrations (Charlie) - Suggestions page web - Benefits page web | Wallet + Net worth chart (Vitto) | Holidays 401k/IRA vehicles (Vitto) - prepare for FE update | 401k/IRA vehicles (Vitto) - prepare for FE update | Badges revisit (TBD) | Badges revisit (TBD) | Home equity vehicle (TBD) | White Label audit (Vitto) Home equity vehicle (TBD) Kids Ed goal (Vitto) - prepare for FE update Other vehicles (Vitto) - prepare for FE update Budget enh (Vitto) - prepare for FE update | Accont Linking (Vitto)
Product | RSU design (Ankita) - Prod Client Questions Journey Helper (Mariano) - Req's Account Linking & detached vehicles (Ankita+Mariano) - Prod support | Journey Helper (Mariano) - Support Year end data story (Mariano) Wellness Score (Leif) - investigation & audit RSU design (Ankita) - Design Support Detached vehicles (Ankita) - Prod support Check out Looker Studio Pro | Journey Helper (Mariano) - Support In-app feeback & article Share (Mariano) - Req's Detached vehicles (Ankita+Mariano) - Prod support RSU design (Ankita) - Design/ Prototype Support Wellness Score (Leif) - address limitations - tech review | Wellness Score (Leif) - Req's In-app feeback & Sharing (Mariano) - Support Savings Vehicle (Ankita) - Prod support Detached vehicles (Ankita) - Prod support ES fixes and stratetgy (Mariano) | Wellness Score (Leif) - Support Insurance & estates. (Ankita) - Research Detached vehicles (Ankita) - Prod Support ES fixes and stratetgy (Mariano) | User content ratings (Mariano) Detached vehicles (Ankita) - Prod Support Insurance & estates. (Ankita) - Research ES implemtnation (Mariano) Review Kogito rules for Journeys | Mariano PTO Mar21-22 Leif PTO Mar26-29 Ankita PTO Mar 15 Quarterly Planning Journeys launch prep UST decks and meetings Detached Vehicles (Ankita) - Prod Support Insurance & estates. (Ankita) - Prod req's | Mariano PTO Apr (8,9),10,11,12 Leif PTO Apr1-2 Ankita resigned Apr9 Journeys UAT and launch prep (Mariano) Quarterly planning UST decks and meetings Insurance & Estates (Leif) - Prod Support Tagging strategy (Leif) | Tagging strategy Dev sup | Elastic search strategy Profile builder - req's Insurance dashboard - design support, client testing Journeys Dev support | Profile builder (Mariano) - Req's Life@ logo change ES Tags re-upload Journeys - Launch support | Profile builder - Req's Detach veh -Dev support | Quarterly Planning + analytics Detach veh -Dev support Page-to-Page UX - Reqs | Quarterly Planning + analytics Detach veh -Dev support Page-to-Page UX - support Content exploration - Benefits - Chatgpt add external links to all content types in CMS | Detach Veh pt 1 UAT -Mariano Profile builder (Mariano) - support Insurance (Leif) - support Page-to-Page UX (Leif) - support Content exploration - Benefits - Chatgpt | Detach Veh pt 1 UAT -Mariano Meta decks (Leif) - Business Review for Mercer - Referall info for Mercer - Semi-annual review Insurance (Leif) - support Page-to-Page UX (Leif) - support Content support - newsletter - push Analytics - Goals usage - Content | Detach Veh pt2 - Support Estates (Leif) - Reqs Page-to-Page UX (Leif) - support Scored questionnaires (Mariano) - Exploration Content exploration - Benefits - Chatgpt | Detach Veh pt2 - Support Estates (Leif) - Support | Detach Veh pt2 - UAT Estates (Leif) - Support FInalizing release (Mariano) wrapping up A1 (Mariano) onboarding UST India | Detach Veh pt2 - UAT Estates (Leif) - Support Quarterly plan FInalizing release (Mariano) wrapping up A1 (Mariano) onboarding UST India | Net worth chart - Wallet (Leif) Wellness Score (Mariano - Reqs |  | Leif PTO Nov4-13 Mariano PTO Oct28-Nov4 |  |  | Quarterly Planning |  | Net worth chart - Wallet (Leif) | Budget enh (TBD) - Nudges (mobile) - more Prep for refreshes (TBD) - Vehicles - Kids Ed | Cost of Sims (TBD) Rent v Buy sim (TBD) | Cost of Sim (Leif) - Req's add external links to all content types in CMS Repurpose Sims for other stories White Label (Leif) - Investigation & Audit Account Linking |  |  |  | Multi-tenancy audit (Vitto) Net worth chart (Ankita) Multi-tenancy handbook/prep (Mariano) | Cost of... sims (TBD) TBD (TBD) Index the Feature pages for 'Search' - keywords on page titles?? Action card tool-tips (Mariano) | Cost of... sims (TBD) Big trip goal (TBD) |  | White Label audit (Vitto) Home equity vehicle (TBD) | Badges revisit (TBD) Account linking (TBD)
User testing |  |  | RSUs | RSUs |  |  | Interdependent goals - review with gauri and create plan User content ratings - checkin with Gauri for plan | User content ratings - heuristic review Interedependent goals - heuristic review | Wellness Score - heurestic review |  |  |  |  | Insurance dashboard - Light testing |  |  | Budget enhance- Light testing
Analytics |  |  | Added data to pipeline -Goals onboarding -Retirement -AppOnboarding -Home refresh -Data for Management dashboard | Add charts to Looker dash - Goal onboarding - Home refresh - App Onboarding | - 6month lookback since roadmap pivot - here - reviewed content entry points & topics - here | Write reqs for Journeys events Monthly analytics report |  |  | Add chart to Looker dash - Journeys | Monthly analytics report
Publications (tracker) |  |  |  | Jackie supporting UST | Jackie supporting UST | Jackie supporting UST | Jackie supporting UST | Jackie supporting UST | Jackie supporting UST
UX content | RSU vehicle (tbd) - Finalize content | Detached vehicles (Jackie) Insurance dashboard (Elijah) - Content Iteration | Detached vehicles (Jackie) - User testing RSU vehicle (Jackie) - Final | Detached vehicles (Jackie) Savings figma completion () | In-app feedback (TBD) | Dynamic Polls conclusion Insurance dashboard (Elijah) - Design Iteration - Prototype | Insurance dashboard (Elijah) - Finalize content | Budget enhance. (Vitto) White Label audit (Vitto)
Research / ED
Motion designer
Communications | [27 empty] | Push notification strategy
Changelog
Note on A1: @suzannevanbeek@roundfeather.com _Assigned to suzannevanbeek@roundfeather.com_ -Leif Drake
Note on D5: @marianoconi@roundfeather.com Hey, Meta asked if we can hide the 'Views' numbers on articles on the web app? We already hide on mobile. This is not super urgent, wondering where we can fit it in... assume it needs to be the A1 team? _Assigned to marianoconi@roundfeather.com_ -Leif Drake

## Release 2025
 | time axis 2024-12-14 to 2025-03-30
 | time axis 2024-12-14 to 2025-03-30
User content ratings (web) | 2025-01-22: Release
Goals refactor & BAC | 2024-12-16: UAT; 2025-01-22: QA
Profile mobile - onboarding + profile | 2025-01-06: QA; 2025-02-25: Stage
Profile web - onboarding | 2025-01-17: QA; 2025-02-25: Stage
Profile web - profile page | 2025-02-12: QA; 2025-02-25: Stage
SSO fail redirect to Paven.io | 2025-02-04: QA; 2025-02-11: Stage; 2025-02-12: submit
article/polls bugs | 2025-02-25: Stage
Null values bug in pipeline | 2025-02-25: Stage
Content gating
Revisitable polls
Wellness score
Vertical article layout
Pre-prod
HSA
Insurance dashboard
RSUs
Estates dashboard

## Releases 2023-4
[169 empty] | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | time axis 2023-08-10 to 2024-01-23
[168 empty] | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | time axis 2023-08-10 to 2024-01-23
Occcam's Web | 2023-08-10: UAT; 2023-08-16: Release (Web)
Home loading & logout bug fix | 2023-08-24: hotfix
Bullet template (web) | 2023-08-17: Dev; 2023-08-21: UAT; 2023-09-20: Release (Web)
Analytics - goals + | 2023-08-23: Dev; 2023-08-29: UAT; 2023-09-20: Release
BAH dash proj fix | 2023-08-21: Dev (BE); 2023-08-29: UAT; 2023-09-15: Submit; 2023-09-20: Release
Editable tip title | 2023-08-25: Dev; 2023-08-30: UAT; 2023-09-15: Submit; 2023-09-20: Release
SSO-friendly links | 2023-08-15: Spike; 2023-08-24: Dev; 2023-08-30: UAT; 2023-09-15: Submit; 2023-09-20: Release
Retirement dashboard | 2023-08-31: Dev; 2023-09-27: QA; 2023-09-28: QA; 2023-09-29: QA; 2023-10-02: QA; 2023-10-03: QA; 2023-10-04: QA; 2023-10-05: UAT; 2023-10-12: Submit; 2023-10-16: Release
Skeleton | 2023-09-29: QA; 2023-10-02: QA; 2023-10-03: UAT; 2023-10-12: Submit; 2023-10-16: Release
App onboarding (mobile) | 2023-10-04: Dev; 2023-11-15: UAT; 2023-12-05: merging with FF booking & bug fixing; 2023-12-14: Submit; 2023-12-18: Release
App onboarding (web) | 2023-10-09: Dev; 2023-11-30: UAT; 2023-12-05: merging with FF booking & bug fixing; 2023-12-14: Submit; 2023-12-18: Release
FF Booking change | 2023-12-21: UAT; 2023-12-28: Submit; 2024-01-01: Release
Suggestion drawer (android) | 2023-12-04: UAT; 2023-12-21: UAT; 2023-12-28: Submit; 2024-01-01: Release
Suggestion drawer (web) | 2023-12-04: UAT; 2023-12-21: UAT; 2023-12-28: Submit; 2024-01-01: Release
Suggestion drawer (iOS) | 2023-12-12: UAT; 2023-12-21: UAT; 2023-12-28: Submit; 2024-01-01: Release
Home & Menu android & BE | 2023-12-26: UAT; 2023-12-28: Submit; 2024-01-01: Release
Home & menu Web | 2023-12-26: UAT; 2023-12-28: Submit; 2024-01-01: Release
Home & Menu iOS | 2023-12-26: UAT; 2023-12-28: Submit; 2024-01-01: Release
Home & Explore enhancements WEB | 2024-01-11: UAT; 2024-01-15: Submit; 2024-01-17: Release
Explore (android) | 2024-01-11: UAT | [9 empty] | Submit |  |  |  |  | Release
Coach (mobile) | 2024-01-11: UAT | [9 empty] | Submit |  |  |  |  | Release
Benefits (mobile) | 2024-01-11: UAT | [9 empty] | Submit |  |  |  |  | Release
Search (mobile) | 2024-01-18: UAT | [9 empty] | Submit |  |  |  |  | Release
Explore/Coach (web) | [183 empty] | UAT | [13 empty] | Release | bar: 2024-01-22 to 2024-01-23
Benefits (web) | [183 empty] | UAT | [13 empty] | Release
Journey helper (mobile/BE) | [217 empty] | UAT | [28 empty] | App submit |  |  |  |  | Release | bar: 2024-01-22 to 2024-01-23
Journey helper (Web) | [217 empty] | UAT | [28 empty] | App submit |  |  |  |  | Release
Search (web)
Bug fixing (BE) | [214 empty] | Fix Kogito rules for goal action card
Bug fixing (Android) | [237 empty] | Life Path bug, App Onboading question text
Bug fixing (iOS and Web) | [237 empty] | Add login in upper right to Splash, give article card carousel button
Analytics - null users | 2023-08-21: Dev
Error handling (FE)
BE action cards enh
EMF goal (detached)
Questionnaires
Account linking
Wallet (detached)
Brokerage (detached)
Checkings (detached)
Buying a Car (detached)
Budget
White Label
RSUs
Insurance
Note on CB18: @sauldiaz@roundfeather.com @marianoconi@roundfeather.com can we please update this calendar for the remaining work with A1? _Assigned to sauldiaz@roundfeather.com_ -Leif Drake

## Cross team plan 2023
| Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33 | Sprint 34 | Sprint 35 | Sprint 36 | Sprint 37 | Sprint 38 | Sprint 39 | Sprint 40 | Sprint 41 | Sprint 42
| Jul 6 - Jul 20 | Jul 20 - Aug 3 | Aug 3 - Aug 17 | Aug 17 - Aug 31 | Aug 31 - Sep 14 | Sep 14 - Oct 5 | Oct 5 - Oct 12 | Oct 12 - Oct 26 | Oct 26 - Nov 9 | Nov 9 - Nov 23 | Nov 23 - Dec 7 | Dec 7 - Dec 21 | Dec 21 - Jan 4
Releases (tentative) |  |  |  | Web-only -Aug17 - Occam's web tbd hot fix - Bug fixes |  | All platforms - Sept 21 Bugs & Analytics & SSO friendly links - Editable Tiptitles - Bullet list template - Improve of buttons positioning on sim - Bug on baH Calculator - Analytics on goals and vehicles - Analytics on Articles |  | All platforms - Oct 20 - Retirement dashboard, Skeleton |  |  |  | All platforms - Dec 18 app onboarding
Key Events & Client support |  |  | Aug 2: Meta benefits team offsite Aug 9: Meta Strategy meeting | Open enrollment prep?? | Sept6 - Meta Strategy meeting | Sept20 - wide channel Meta announcement Sept 27 - semi annual review with Julie and Kaye | Oct 16 - Tax filing extension deadline | Open Enroll opens Oct 23 | RSU Nov1-30 (Nov15 vesting) Announce new 401k limits TBD | Open Enrollment end Nov 10 |  | Deloitte deprecated Dec7 | FF booking launch Jan1
A1 Maint. Eng (roughly) |  |  | Pending SoW | Bugs fixing - proj error, etc Fix temporal user_id issues Small enhancements - Tip title | Retirement dashboard Article fixes | Retirement dashboard cont'd Analytics fixes Skelton and loading | Retirement & Skelton App onboarding | App onboarding - cont'd Retirement (Web) | App onboarding - cont'd Suggestion drawer iOS | Suggestion drawer Andr/web | Home & Main Menu Suggestion drawer Web / iOS | Home & Main Menu | Home & Main Menu Bug fixing contract ends Dec31
RF Engineering |  |  | iac Upgrade - Auth0 Tenent config Bug fixing SSO friendly links (Vishal) | SSO friendly links - Spike iac Upgrade -Github stack improvement | Vishal PTO Aug31-7 JD PTO Sept13 Release Sept 7 or 12 Meta assessment (JD) SSO friendly links (Vishal) FF booking plans (JD) | JD PTO Sept14-18 Release prep SSO friendly links Analytics QA steup: null users Update collge costs (Vishal) Key inventory upgrade (Vishal) | Buying a Car spike SSO friendly links ES strategy & plan Faster pipeline to Prod | Data pipeline: goals & Notif. One Signal: automate load, more tags General Infra improvements | Booking integration FF Web Deployment changed Improved monitoring | Booking integration FF Detailed Error Logging Improved monitoring | FF booking flow (Vishal +) Pre-prod enviro (Mahesh +) Detach vehicn arch (Mladen) | Analytics pipeline (JD) - Vehicles, Session, Goals, Home/Featured, Content Pre-prod enviro (Mahesh +) Detach vehic arch (Mladen) | Pre-prod enviro (Mahesh +) Detach vehic (Mladen) Vacation Mladen / Vishal
Design | App Onboarding: (Suri) - Problem definition Design Library Maintenance (Suri) - Handoff checklist - Define key processes - Detail New design hand off Rent Vs Buy (Suri) -Prototype adjustments Resiliance Badges (Charlie) - Finanlize Prototype - Usability Testing - Feedback incorporation - Motion for Badges | App Onboarding: (Suri) - Design Exploration - Prototype Design Library Maintenance - Prioritize Key Processes Resiliance Badges (Charlie) - Finalize design (mobile) Rent Vs. Buy (Charlie) - Create Illustrations | App Onboarding (Suri): - User testing - Finalize mobile Resiliance Badges (Charlie) - Finalize design (web) Skeleton & Loading screen improvement (Charlie) - Lottie Files - Animations | App Onboarding (Suri): - Finalize web Suggestion drawer UX (Mariano) - Internal expert review (Sebas) Suri work remote from WI Home Layout Enhacements (Charlie) - Problem defintion - Design Iteration Charlie PTO (Aug18-22) | App Onboarding (Suri): - Incorporate ED feedback Suggestion drawer UX (Suri) - Finalize enhancements Home Layout Enhacements (Charlie) - Prototype - User Testing | Saul PTO Sept 26-28 Home layout (Charlie & Suri) - Finalize design App onbarding (Suri) - Figma documentation | Vitto returns to Paven Suri goes to Bayada Saul PTO Sept28-Oct4 Home layout (Charlie & Suri) - Explore, Main Menu, user Testing Case study (Charlie/Suri) - Nicky project | Home layout (Charlie & Suri) - Finalize design Journey Helper (Vitto) - Exploration" Case study (Charlie/Suri) - Nicky project | Charlie PTO Nov2-3 Journey Helper - Finalize design Buying a car (Charlie) - Design exploration | Buying a car (Charlie) - Finalize design Journey Helper (Vitto) -Design iteration Home layout (Vitto) - Dev Support | RSU vehicle (Charlie) - Design exploration Journey Helper (Vitto) -User testing -Iteration design | Charlie went to Bayada Journey Helper (Vitto) -User testing | Journey Helper (Vitto) -Iteration design Account Linking & Detached vehicles (Vitto) Buying a car (Charlie) - Figma doc
Product |  | Home Layout - Requirement Definition - Feature clarification Skeleton & Loading screen - Requirement Definition - Feature clarification App Onboarding (Leif) - product support Badges support (Leif) - Support | Home Layout (Mariano) - Requirement Definition - Feature clarification Badges (Leif) - product support App Onboarding (Leif) - product support | Mariano in CA Aug17-26 Home Layout (Mariano) - Product support Suggestion drawer UX (Mariano) - Support expert review & req's | Mariano PTO: Tues5,6,7,8, Mon11,12,13,14 Home Layout (Leif) - Product support Suggestion drawer UX (Mariano) - Support expert review & req's | Mariano PTO: Sept 19 Home Layout (Mariano) - Product support Suggestion drawer UX (Mariano) - product support | Leif PTO Oct3-Oct12 Journey Helper (Mariano) - Requirement Definition - Feature clarification ES Strategy (Leif+Mariano) -kickoff meeting RSU vehicle (Ankita) - Research | Leif PTO Oct12-Oct15 Journey Helper (mariano) - Design support ES strategy (Leif) - Planning Buying a car goal (Leif) - Req's definition RSU vehicle (Ankita) - Req definition | Jounrney Helper (mariano) - Design support Buying a car goal (Leif) - Prod support RSU vehicle (Ankita) - Req definition | Buying a car goal (Leif) - Prod support Account Linking & Detached vehicle (Leif+Ankita) - Exploration | Ankita PTO Nov17-25 Journey Helper (Mariano) RSU vehicle (Ankita) - Prod support Account Linking & detached vehicles (Ankita+Mariano) - Req. Definition | Journey Helper (Mariano) RSU vehicle (Ankita) - Prod support Account Linking & detached vehicles (Ankita) - Req. Definition ES strategy (Mariano) - fixes + documentation | RSU design (Ankita) - Prod Client Questions Journey Helper (Mariano) - Req's Account Linking & detached vehicles (Ankita+Mariano) - Prod support
User testing | [10 empty] | Journer Helper - User testing | RSU vehicle - Heuristic review Account linking & Inter Goals Kickoff
Analytics |  |  | Add wellness score (JD) Create basic goal dashboards (Mariano) Understand return freq behavior (weekly, monthly, etc) Add baseline #s for OKRs (Leif) | Clean up dashboard to improve load time |  | - Raw FinWell score data | *Update dashboards for: - Goals - Notifications |  |  | Update dashboard to reflect new Onboarding |  | Management dashboard - Req's
Publications (tracker) |  |  | Aug15: Wellthy: How to play your cards with elder care costs Aug 17: Goals 2 | Aug 22: New investing 2 Aug 24 Lifemoments 2 Aug 29: Sector Play 2 | Aug 31: Benefit Spotlight 2 Sep 5: Timely Dispatch 3 Sep 7: Benefit trends 3 Sep 12: Benifit Strategy 3 | Sep 14: Goals 3 Sep 19: New investing 3 Sep 21: Life moments 3 Sep 26: Sector play 3 | Sep 28: Benefits Spotlight 3
UX content | Resiliance Badges: (Elijah) - Finanlize Content App Onboarding (Jackie) -Review plan | Reilience badges (Elijah) - finalie content App Onboarding (Jackie) - Content Exploration | App Onboarding (Jackie) - Finalize content Skeleton Content (Elijah) Home layout (Elijah) - Problem definition | Home layout (Elijah) - Content exploration Suggestion drawer UX (TBD) - Problem definition support | App Onboarding (Jackie): - Incorporate ED feedback Home layout (Elijah) - Content iteration Suggestion drawer UX (Eric) - Content support | Home Layout (Elijah) - Finanlize Content Suggestion drawer UX (Eric) - Content support | Jackie PTO Oct 10,11 Journey Helper (TBD) - Content exploration Home Layout (Elijah) - Explore, Menu, etc | Jackie PTO Oct 12-30 Journey Helper - Content iteration | Journey Helper (Elijah) - content iteration Buying a car - Content exploration | Journey helper (Elijah) - Finalize content Buying a car (tbd) - Iteration | RSU vehicle (Jackie) - Content iteration Journey Helper (Elijah) - Content | RSU vehicle (Jackie) - Finalize content Journey helper (Elijah) - Content | RSU vehicle (tbd) - Finalize content
Research / ED |  |  | Badges: - ED design reviews App onboarding: - ED design reviews | App onboarding: - ED design reviews | Home layout: - ED design reviews | Journey Helper - followup questions on brief Rushil PTO wk of Sept18 | Buying a car - Req's review | Journey Helper - ED design reviews Buying a car - ED design reviews |  | Insurance dashboard - ED brief or Reqs review | RSU vehicle - Design review Insurance dashboard - ED design reviews
Motion designer | Resiliance Badges: - Motion | Rent v Buy - Motion | Badges - Nadia/Zohreh consulting |  |  | Lottie for onboarding - Nadia/Zohreh | Badges - Nadia/Zohreh |  |  |  | Journey Helper - Motion
Communications |  |  | Email: Push: Workplace: | - Meta Posts (traffic focus) - Date on posts and names
Changelog |  |  | -Resilience badges carried over and pushed Home layout kickoff back by 1sprint -Moved Buying a car ahead of Insurance dashboard due to Nicky's feedback on bizplan roadmap Moved A1 start back to Aug17, which pushed back release dates. Moved Insurance dashboard back 1sp to give more space to Home layout
Note on A1: @suzannevanbeek@roundfeather.com _Assigned to suzannevanbeek@roundfeather.com_ -Leif Drake

## Detach veh plan after Apr
| A1 FE (sprint) | A1 BE (sprint) | RF BE (sprint) | Months |  | Notes
Break apart BaH - adjust calls for brokerage | 1 | - |  |  |  | April
Break-apart Retirement - adjust calls for all retirement vehicles | 2 | - |  |  |  | May
Brokerage visuals - graph & assign goal | 2 | - |  |  |  | June: might reduce effort for chart based on POCs around Apr10
Release 1 | 5 |  |  | 2.5 | Aug
First new vehicle prep | 1 |  | 1.5 |  |  | 1 BE resource | Estimates need to be redone given the delays experienced in Release 1
Checkings implementation | 1 |  | 1.5 |  |  | the input/UI is almost identical to Brokerage
Savings implementation | 1 |  | 1.5 |  |  | the input/UI is almost identical to Brokerage
First new goal prep | 1 |  | - |  |  | define the logic of for a given vehicle, which goal do we use it for first?
EMF goal - setup and dashboard | 1 |  | 1.5 |  |  | Padding
Release 2 | 5 | 0 |  | 2.5 | Oct
Wallet - add account, vehicle list | 1.5 |  | 0
Budget - change list of goals to vehicles | 1 |  | 0
New vehicle cards | 0.75 | 0 | 0
Release 3 | 3.25 |  |  | 1.625 | Nov
RSUs implementation | 1.5 |  | TBD
BAC goal - setup and dashboard | 1 | 1 | TBD
Release 4 | 2.5 |  |  | 1.25 | Jan
401k, IRA visuals - line graphs in goalless state |  |  | 0
Post-retirement visuals - graph |  |  | 0
529 visuals - graph
Loved ones visuals - graph
HSA vehicle implementation
SS vehicle implementation
Note on A3: @mladen.kliska@roundfeather.com Hey, just wanted to make sure you've seen this, so we can discuss in the meeting today _Assigned to mladen.kliska@roundfeather.com_ -Leif Drake

## OKRs - baselines
Metrics | Mission | Objective | Drivers | 2Q22 | 3Q22 | 4Q22 | 1Q23 | Factors | 2Q23 Actual | Factors | 3Q23 Goal | 3Q23 Actual | Factors | 4Q23 Goal | 4Q23 Actual | Accuracy | Factors | 1Q24 Goal | 1Q24 Actual | Accuracy | Vs prev Q | Factors | 2Q24 Goal | 2Q24 Actual | Accuracy | Vs prev Q | Factors | 3Q24 Goal | 3Q24 Actual | Accuracy | Vs prev Q
Notes on season and bigger context | [7 empty] | Layoffs No beneift comms No hiring |  | Summer vacations Minimal benefit comms Slow hiring |  |  | Open Enrollment Holiday slowdown Slow hiring |  |  |  | New FF booking Start of tax season |  |  |  |  | End of tax season Apr17 companywide post |  |  |  |  | no major comms planned
New users | Reach of impact | Increase adoption | -comms | 1427 | 1105 | 939 | 754 | One signal | 459 | Branch.io links Workplace Group FYI People post | 1000 | 684 | SSO friendly links WP group promotion | 1000 | 428 | -57.2% | Cross promos with other benefit providers External links in WP posts | 700 | 596 | -14.86% | 139.3% | Share journeys | 829.9439 | 638 | -23.13% | 7.047% | expect slow hiring in summer | 733.7 | 468 | 936.8 | 843.755
Unique users | Reach of impact | Increase engagement frequency | -comms -email & push | 2175 | 1984 | 2047 | 2249 |  | 1638 | Workplace Group FYI People post | 2300 | 1919 |  | 2300 | 1777 | -22.74% | Home Layout App Onboarding Suggestion drawer | 2250 | 1808 | -19.64% | 101.7% | Home layout Journeys | 2350.4 | 1695 | -27.88% | -6.25% |  | 1949.25 | 1483 | 2018.6 | 2241.6375
Total sessions | Reach of impact | Increase engagement frequency |  | 4070 | 3602 | 4038 | 5052 | Polls | 3596 | Email newsletter | 4300 | 4694 | Email newsletter | 4300 | 3254 | -24.33% | Home Layout App Onboarding Email newsletter | 5625 | 4574.24 | -18.68% | 140.6% | Journeys | 7730.4656 | 4192 | -45.77% | -8.356% | Journeys | 4820.8 | 3314 | 4071.6 | 5543.92
Avg sessions in qrtr | Reach of impact | Increase engagement frequency |  | 1.87 | 1.82 | 1.97 | 2.25 |  | 2.02 | Notifications Workplace group | 1.9 | 1.84 |  | 2 | 1.87 | -6.5% | Home Layout App Onboarding Suggestion drawer | 2.5 | 2.53 | 1.2% | 135.3% | Journeys | 3.289 | 2.47 | -24.9% | -2.372% | Journeys | 2.8405 | 2.23 | 1.986 | 3.2666
Time in app in qrtr (Avg / min) | Reach of impact | Increase engagement depth | -content -usability (loading, nav, onboarding) | 3:46 | 3:46 | 3:09 | 3:16 |  | 3:00 | New content More benefit content | 3:23 | 3:16 | BAH Goal Brokerage New content More benefit content | 3:45 | 3:35 | -4.444% | Home Layout App Onboarding Suggestion drawer | 4:00 | 4:03 | 1.25% | 113% | Journeys ES fixes | 4:45 | 3:44 | -21.4% | -7.819% | Journeys | 4:17 | 3:27 | 3:23 | 0.20524
Avg content reads per user | [8 empty] | 1.08 |  | 1.3596 | 0.91 |  | 1.035 | 1.45 | 40.1% | Home Layout App Onboarding Suggestion drawer | 2.2 | 2.48 | 12.73% | 171% | Journeys ES fixes | 3 | 2.44 | -18.67% | -1.613% | Journeys | 2.806 | 1.97 |  | 3.2269
Total opens of content | FinWell & reducing stress | Increase finwell through learning | -new users -new content | 4180 | 3437 | 2805 | 3116 | Dark/light | 2101 | More notifications FYI People post Polls Dark/light | 3127 | 1500 | App onboarding | 2380.5 | 3285 | 38% | Home Layout App Onboarding Suggestion drawer | 4950 | 4483.84 | -9.417% | 136.5% | Journeys ES fixes Search fixes | 7051.2 | 4132 | -41.4% | -7.847% | Journeys | 4751.8 | 2918 | 3127.8 | 5464.57
Total opens of benefit content | FinWell & reducing stress | Increase finwell through learning | -quality of content -relevancy of content | 1717 | 1312 | 853 | 677 |  | 491 |  |  | 388 | Tip title | 602.25 | 1237 | 105.4% | Suggestion drawer Newsletter | 1500 | 1415 | -5.667% | 114.4% | Journeys ES fixes | 1618.6136 | 1181 | -27.04% | -16.54% | Journeys | 1358.15 | 665 | 1010 | 1561.8725
Benefit content per user | [17 empty] | 0.66667 | 0.78263 |  |  |  | 0.68865 | 0.69676 |  |  |  | 0.80127 | 0.44842 |  | 0.92146
Overall Suggestions (avg clicks per user) | FinWell & reducing stress | Tip over intent-to-action gap through learning | -quality of content -relevancy of suggestion | 1.25 | 1.46 | 0.96 | 0.72 |  | 0.46 |  |  | 0.51 | - benefit | 0.82812 | 0.77 | -7.019% |  | 1 | 1.14 | 14% | 148.1% |  | 1.368 | 0.73 | -46.64% | -35.96% |  | 0.8395 |  | 0.97 | 0.96542
Benefit Redirects (avg clicks per user) | [11 empty] | 0.17 |  | 0.25 | 0.36 | 44% |  | 0.45 | 0.45 | 0% | 125% |  | 0.5625 | 0.29 | -48.44% | -35.56% |  | 0.3335 |  |  | 0.38352
Benefit redirects | Benefits awareness & Utilization | Increase benefits utilitization |  | 1996 | 1859 | 1010 | 795 |  |  | Hyperlinks Occam's |  |  |  |  | 628 |  | App onboarding | 700 | 818 | 16.86% | 130.3% |  | 1322.1 | 483 | -63.47% | -40.95% |  | 555.45 |  | 1415 | 638.7675
Chats started | Benefits awareness & Utilization | Increase benefits utilitization |  | 329 | 365 | 229 | 231 |  | 155 |  |  |  |  | 200 | 195 |  |  | 250 | 259 | 3.6% | 132.8% |  | 310.8 | 130 | -58.17% | -49.81% |  | 149.5 |  |  | 171.925
Booking opens | [17 empty] | 300 | 370 | 23.33% |  |  | 300 | 236 | -21.33% | -36.22% |  | 271.4 |  |  | 312.11
Bookings confirmed | Benefits awareness & Utilization | Increase benefits utilitization |  | 714 | 600 | 266 | 245 |  | 90 |  |  | 72 |  | 50 | 22 | [7 empty] | 0
Avg goals per user |  |  | -discoverability -usability - #/type of goals | [6 empty] | BAH goal |  | 2.58 | BAH goal App onboarding | 3 |  |  | App onboarding Home Layout
Log-in fail rate |  |  |  |  | 8% | 14% | 23% |  | 25% |  | 3% | 12% | Auth0 (Aug15) Web logout fix | 3% | 19% | [14 empty] | 0.175
Avg number of goals setup per user | FinWell & reducing stress | Increase finwell by planning | -discoverability -usability |  |  |  | 1.2 |  |  | Debt goal BAH goal | 2.2 |  | Retirement dashboard |  |  | #DIV/0! |  |  |  | #DIV/0! |  |  |  |  | #DIV/0! |  |  |  |  | 1.2
All-time user's since Launch Mar 2022 | [14 empty] | 8632 |  |  |  | 9125
Users in Dormant (12mos+ since last activity) | [8 empty] | 1307 |  | 2045 |  |  |  | 40.38% | #DIV/0! | -15% | 25.38% | 48.05% | 89.31% |  |  |  |  | #DIV/0!
Users in Disengaged (180-365days) | [8 empty] | 2220 |  | 888 |  |  |  | 24.8% | #DIV/0! | -10% | 14.8% | 20.62% | 39.33% |  |  |  |  | #DIV/0!
Users in Inactive group (90-180days) | [8 empty] | 1157 |  | 262 |  |  |  | 14.79% | #DIV/0! | -5% | 9.794% | 11.95% | 21.97% |  |  |  |  | #DIV/0!
Users in Active (30-90days) | [10 empty] | 524 |  |  |  | 13.43% | #DIV/0! | 15% | 28.43% | 11.55% | -59.37% |  |  |  |  | #DIV/0!
Users (7-30days) | [14 empty] | 4.194% |  | 10% | 14.19% | 5.984%
Users in lat week (1-7days) | [14 empty] | 2.398% |  | 5% | 7.398% | 1.841%
Users not signed up | [8 empty] | 48740 |  | ? |  |  |  |  | #DIV/0! |  |  |  | #DIV/0! |  |  |  |  | #DIV/0!
Unique opens of benefit content | Benefits awareness & Utilization | Increase benefits awareness | -new users -sessions -new benefit content | [6 empty] | Polls Dark/light | [5 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  |  | #DIV/0! |  |  |  |  | #DIV/0!
Avg number of vehicles setup per user | FinWell & reducing stress | Increase finwell by planning | -usability | [6 empty] | Brokerage | [5 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  |  | #DIV/0! |  |  |  |  | #DIV/0!
Artcle opens on goal pages |  |  |  |  | 2058 | [10 empty] | #DIV/0! |  |  |  | #DIV/0! |  |  |  |  | #DIV/0! |  |  |  |  | 2058
Avg number of simulator completion | [9 empty] | Occam's | [5 empty] | #DIV/0! | Buy vs Rent Entry point |  |  | #DIV/0! |  | Buy vs Rent Entry point |  |  | #DIV/0! |  |  |  |  | #DIV/0!
Median wellness score (for users over 30) | FinWell & reducing stress | Increase finwell by planning | -usability | [6 empty] | Debt goal Brokerage |  |  | Retirement goal |  |  |  | EMF goal |  |  |  |  | EMF goal | [7 empty] | #DIV/0!
Clicking suggestion in drawer | Benefits awareness & Utilization | Increase benefits utilitization |  | - | - | - | - | [9 empty] | Suggestion drawer UX |  |  |  |  | Suggestion drawer UX | [7 empty] | #DIV/0!
Goals added
Goal onboarding completion rate |  |  |  | NA | NA | NA | NA |  | NA |  | TBD | TBD
Goal events |  |  |  | NA | NA | NA | NA |  | NA |  | TBD | TBD
[7 empty] | One Signal | New Chat New Booking |  | Auth1
Polls usage |  |  |  | meta+null
Hyperlink usage
% of users with Retirement goal setup
% of users with BAH goal setup
% of users with EMF goal setup
% of users with Debt goal setup
% of users with Kids ed goal setup
% of users with VEHICLE setup
8632
Users in Dormant (12mos+ since last activity) | [14 empty] | 3486 | 40.38% |  |  |  | 0% |  |  |  |  | 0%
Users in Disengaged (180-365days) | [14 empty] | 2141 | 24.8% |  |  |  | 0% |  |  |  |  | 0%
Users in Inactive group (90-180days) | [14 empty] | 1277 | 14.79% |  |  |  | 0% |  |  |  |  | 0%
Users in Active (30-90days) | [14 empty] | 1159 | 13.43% |  |  |  | 0% |  |  |  |  | 0%
Users (7-30days) | [14 empty] | 362 | 4.194% |  |  |  | 0% |  |  |  |  | 0%
Users in lat week (1-7days) | [14 empty] | 207 | 2.398% |  |  |  | 0% |  |  |  |  | 0%
Note on L3: we set this number because we had achieved it in 3Q & 4Q of 2022. 2023 has been abnormally low, esp 2Q23 -Leif Drake
Note on X3: Assuming we carry over 39% growth from Q4->Q1 -Leif Drake
Note on AC3: 15% increase from 2Q24 -Leif Drake
Note on L4: This is our quarterly avg since launch (2019) + 15% -Leif Drake
Note on L5: This is our quarterly avg since launch (4072) + 15% -Leif Drake
Note on L6: just a function of the other KRs (4300/2300) -Leif Drake
Note on L7: maintain the average since launch (3:23) -Leif Drake
Note on L9: realistically, achieving the quarterly average per quarter is worthy (31217) -Leif Drake
Note on O9: rolling avg of last 4 quarters -Leif Drake
Note on O10: rolling avg of past 4 quarters -Leif Drake
Note on O12: Avg of last 4 quarters + 25% -Leif Drake
Note on A24: @marianoconi@roundfeather.com instead of focusing on 'New users' only, it would be helpful if we could measure and track these groups of users based on last activity. I know we've talked about this before, but let's revisit _Assigned to marianoconi@roundfeather.com_ -Leif Drake

## Rationale for 2H24 projects
| Docs | Improves FinWell value prop | Improves Benefits value prop | Closes gap with competitors | Creates a differentiator | Invests where we see traction | Small scope | Reusable, platform feature
Interdependent goals | Product docs | Yes | No | Today, Paven’s goals and vehicles are siloed, so the user can’t plan holistically, which is a major gap compared with other financial wellbeing and planning apps. This project removes those silos so vehicles/savings can be flexibly applied to multiple goals, better reflecting the real world. | No | No | No | Yes, will speed up the addition of new goals and vehicles
EMF goal dashboard | Product docs | This goal is critical to our financial wellbeing philosophy, and this project will apply Interdependent goal logic, address some pressing UX limitations, and update the look & feel to match the rest of the app. | No | Yes | No | No | Yes | Not really, but it does serve as next 'existing' goal to apply Interdepdendent goal logic
Buying a car goal |  | Today, most of Paven’s features (in particular our goals) take a long time horizon, which requires less visits and interactions within our app. This projects looks to increase engagement and takes a short term horizon, and will start to create a better mix of long-term and short-term. Buying a car is one of the largest purchases that people make, and this feature will help with that, along with our content series on the topic. | No | Yes | No | No | Yes | Not really, but it does serve as first 'new' goal to apply interdepednent goal logic
RSUs | Product docs | Yes | This project is an investment in a key benefit from the employer, RSUs | This project addresses a gap with competitors, who have features on RSUs and equity compensation | No | RSUs, which is also the most popular topic for articles in Paven. | Yes | Not really, but it serves as first 'new' vehicle to apply interdependent goal logic
Wellness Score in UI |  | Yes | No | Yes | Possibly highglights differences in our | We haven't written about this, so no sense of user traction but Meta stakeholders liked the idea | Yes | Yes, we can continue to refine and improve the score in background as we add goals and other criteria
User ratings of content | Product docs coming by Feb2 | Yes | Yes | No | No | No | Yes | This project will give us ongoing, actionable insights into what content/topics users find most helpful, so that we can invest our content resources with the most impact.
Questionnaires | Product docs | Yes | Yes | Today, Paven does not collect enough information about the user to understand their whole financial picture, which makes it harder to offer credible guidance or deliver on our key value propositions: personalization of the app (content/actions) and evaluation of Financial Wellbeing. | Yes, we can get into new areas that aren't covered by competitors | No | Yes | These questionnaires will give us the basis to gather this information; it will also enable us to request product feedback (critical to roadmap decisions) and showcase recent releases in a new way (increase engagement).
Insurance dashboard | Product docs This feature gives users a consolidated view of their various insurance policies and estate plans. | It extends Paven into an important area of both FinWell generally and Employee Benefits: Insurance and Estates, | Yes | No | Yes | Takes advantage of our existing library of content on this topic. It also will allow us to differentiate from and gain an advantage over competitors that focus on Budgeting, Net Worth, Investing, or Goal Setting | Yes | Not really, but we do hope to build on this feature if it gets traction
BE improvements for Action cards |  | No | No | No | No | No | ?? | Improves the loading performance and stability of the app
Action card tooltips | 2sp design 1.5sp Eng
Budget Nudges (mobile) | 1sp Design 2sp Eng
401k/IRAs/529 | 1sp Design 2.5sp Eng
Other vehicles (Post-Ret work, FinAid, etc) | 1sp Design 2.5sp Eng
Net worth chart in Wallet | 2sp Design 1-2sp Eng
Kids ed goal | 0.5sp Design 1sp Eng
Multitenancy App audit | 1sp Design 1sp Product
Cost of...' sim | 2-3sp Design 2-3sp Eng
New Goal - Big trip | 1sp Design 1sp Eng
Rent vs Buy sim | 1sp Design 2-3sp Eng
Home equity vehicle | 2sp Design 2sp Eng
Badges | 1-2sp Design 3-4sp Eng | how does it fit with Journeys? Wellness Score
Account Linking | 2sp Design 2sp Eng
Index goal dashboard and vehicle details and budget/Life Path for Search results | 0.5 Design 1.5sp Eng
Social Security / Pension vehicle | 2sp Design 2sp Eng
Loan vehicle | 2sp Design 2sp Eng
Notiication center | 2sp Design 2sp Eng
Budget enhancements | 2sp Design 2sp Eng | time-limited Expenses
Note on A17: We should prepare the UX for the potential new client. i.e. -Mariano Coni